## Projects
Project | Manager | Planned % | Actual % | Budget | Actual Cost | Delay Days | Risk Score | Approved By
freedom | Alex | 50 | 48 | 50000 | 45000 | 0 | 1 | Mike Johnson (Project Manager)
ATT | Bob | 70 | 65 | 80000 | 78000 | 2 | 2
redone | Diana | 90 | 90 | 120000 | 115000 | 0 | 1
tuntalk | Ethan | 40 | 30 | 45000 | 48000 | 7 | 4

## Achievements
Project | Achievement
freedom | Project charter approved and kickoff completed successfully.
ATT | Staging environment configuration finalized and verified.
redone | Phase 1 user acceptance testing successfully concluded.
tuntalk | Vendor integration contracts finalized and signed.

## Risks
Project | Risk Description | Probability | Impact | Mitigation
tuntalk | API documentation delays from vendor | High | High | Escalate to vendor management and setup daily syncs.

## NextSteps
Project | Task | Owner | Deadline
freedom | Setup Git repository and configure CI/CD pipeline | Alex | 2026-06-20
ATT | Deploy initial sandbox build for security review | Bob | 2026-06-22
redone | Initiate Phase 2 frontend development modules | Diana | 2026-06-18
tuntalk | Establish connection sandbox with vendor gateways | Ethan | 2026-06-21

## Decisions
Project | Decision Required | Context | Options | Recommendation
tuntalk | Select alternative API gateway vendor | Current vendor is unresponsive on SLA terms. | Vendor A / Vendor B | Migrate to Vendor B immediately.

## Approvals
Timestamp | Approved By | Approved Projects
2026-06-15 23:59:10 | Mike Johnson (Project Manager) | freedom